## A. Toilet monitoring
Nakuru Water and Sanitation Services Company (NAWASSCO)
Project Progress Monitoring by Water Service Providers and Project Task Teams | [20 empty] | Sheet no. |  | 1
Monitoring Sheet |  | Month | >>> | January
A | Monitoring of SafiSan toilet construction: | Day | >>> | 23
Activity |  | Week no. | >>> | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
1 | Plots and household visits carried out | No. | Week | 23 1: 0; 23 2: 3; 23 3: 3; 23 4: 2; 23 5: 5; 23 6: 6; 23 7: 0
|  | No. | Total | 0 | 3 | 6 | 8 | 13 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19
2 | Toilet applications received | No. | Week | 23 1: 3; 23 2: 8; 23 3: 3; 23 4: 4; 23 5: 5; 23 6: 6; 23 7: 0; 23 8: 0
|  | No. | Total | 3 | 11 | 14 | 18 | 23 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29
3 | Toilets ordered | No. | Week | 23 1: 1; 23 2: 8; 23 3: 3; 23 4: 4; 23 5: 5; 23 6: 6; 23 7: 0; 23 8: 0
|  | No. | Total | 1 | 9 | 12 | 16 | 21 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27
4 | Toilets under construction | No. | Week | 23 1: 2; 23 2: 8; 23 3: 3; 23 4: 4; 23 5: 5; 23 6: 6; 23 7: 0; 23 8: 0
|  | No. | Total | 2 | 10 | 13 | 17 | 22 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
5 | Toilets completed | No. | Week | 23 1: 3; 23 2: 8; 23 3: 3; 23 4: 4; 23 5: 5; 23 6: 6; 23 7: 0; 23 8: 0
| (incl. hand-washing facility, landscaping & manual) | No. | Total | 3 | 11 | 14 | 18 | 23 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29
6 | Toilets approved by the WSP | No. | Week | 23 1: 0; 23 2: 8; 23 3: 3; 23 4: 4; 23 5: 5; 23 6: 6; 23 7: 0; 23 8: 0
|  | No. | Total | 0 | 8 | 11 | 15 | 20 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
7 | Subsidies paid | No. | Week | 23 1: 0; 23 2: 8; 23 3: 3; 23 4: 4; 23 5: 5; 23 6: 6; 23 7: 0; 23 8: 0
|  | No. | Total | 0 | 8 | 11 | 15 | 20 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
8 | Toilet data collected | No. | Week | 23 1: 0; 23 2: 8; 23 3: 4; 23 4: 4; 23 5: 6; 23 6: 6; 23 7: 0; 23 8: 0
|  | No. | Total | 0 | 8 | 12 | 16 | 22 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
| TOTAL: | No. | Week | 9 | 59 | 25 | 30 | 41 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL: | No. | Total | 9 | 68 | 93 | 123 | 164 | 212 | 212 | 212 | 212 | 212 | 212 | 212 | 212 | 212 | 212 | 212 | 212 | 212 | 212 | 212
| Overall target: | No. | (*) | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 450 | 450 | 450 | 450 | 450 | 450 | 450
| Percentage of target achieved: | % |  | 3 | 22.6667 | 31 | 41 | 54.6667 | 70.6667 | 70.6667 | 70.6667 | 70.6667 | 70.6667 | 70.6667 | 70.6667 | 70.6667 | 47.1111 | 47.1111 | 47.1111 | 47.1111 | 47.1111 | 47.1111 | 47.1111
|  |  | *): | 23 1: It is possible to change the target during the course of the project

## B. Social marketing
Nakuru Water and Sanitation Services Company (NAWASSCO)
Project Progress Monitoring by Water Service Providers and Project Task Teams | [20 empty] | Sheet no. |  | 1
Monitoring Sheet |  | Month | >>> | January
B | Monitoring of social marketing: | Date | >>> | 23
Activity |  | Week no. | >>> | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
1 | Plots and household visits planned | No. | Week | 23 1: 0; 23 2: 8; 23 3: 14; 23 4: 4
|  | No. | Total | 0 | 8 | 22 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
2 | Plot & household visits carried out | No. | Week | 23 1: 3; 23 2: 8; 23 3: 14; 23 4: 4
|  | No. | Total | 3 | 11 | 25 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29
3 | Barazas planned | No. | Week | 23 1: 1; 23 2: 1; 23 3: 2; 23 4: 4
|  | No. | Total | 1 | 2 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
4 | Barazas implemented | No. | Week | 23 1: 1; 23 2: 8; 23 3: 1; 23 4: 4
|  | No. | Total | 1 | 9 | 10 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
5 | SafiSan Mini Fairs planned | No. | Week | 23 1: 1; 23 2: 0; 23 3: 1; 23 4: 4
| (incl. hand-washing facility, landscaping & manual) | No. | Total | 1 | 1 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
6 | SafiSan Mini Fairs implemented | No. | Week | 23 1: 1; 23 2: 0; 23 3: 1; 23 4: 4
|  | No. | Total | 1 | 1 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
7 | "How to use the toilet" visits planned | No. | Week | 23 1: 0; 23 2: 0; 23 3: 0; 23 4: 4
|  | No. | Total | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
8 | "How to use the toilet" visits implemented | No. | Week | 23 1: 1; 23 2: 0; 23 3: 0; 23 4: 4
|  | No. | Total | 1 | 1 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| TOTAL: | No. | Week | 8 | 25 | 33 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL: | No. | Total | 8 | 33 | 66 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98

## C. DTF construction
(…) Water and Sanitation Services Company
Project Progress Monitoring by Water Service Providers and Project Task Teams
Monitoring Sheet | [11 empty] | Sheet no. |  | 1
C | Monitoring of DTF construction (*) |  | Date | >>> | 2001-01-01 | 2008-01-01 | 2015-01-01
No. | Activity **) | Remarks | Week no. | >>> | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
1 | Assessment of need for DTF(s) |  | Status | 1/2/3/4
2 | Initial site identification |  | Status | 1/2/3/4
3 | VST session |  | Status | 1/2/3/4
4 | Site visit |  | Status | 1/2/3/4
5 | Site availability assessment |  | Status | 1/2/3/4
6 | Site approval (by WSP) |  | Status | 1/2/3/4
7 | Site securing |  | Status | 1/2/3/4
8 | Baraza |  | Status | 1/2/3/4
9 | Mobilisation of Contractor |  | Status | 1/2/3/4
10 | Ground breaking |  | Status | 1/2/3/4
11 | Laying of foundation works |  | Status | 1/2/3/4
12 | Construction works |  | Status | 1/2/3/4
13 | Landscaping & completion works |  | Status | 1/2/3/4
14 | Final inspection & snag list |  | Status | 1/2/3/4
15 | Commissioning |  | Status | 1/2/3/4
*): | This sheet can only be used to monitor the construction of a single DTF |  | Status: | 1 = planned; 2 = initiated; 3 = started/on-going; 4 = completed
**): | The WSP/PTT should add or remove activities if deemed necessary